## Details
Type of Risk | Location | Description of Risk | Probability of Failure | Impact of Failure | Est Cost of Failure | Risk Level | Remediation Status | Component or Application | Device Type | Redundant | Other Affected Components | Risk First Reported | Proposed Action | Target Date | Assigned To | Next Actrion | Due Date | Date Last Modified

## Summary
Type Of Risk | Location | Number of Devices | Risk Assessment Findings | Probability of Failure | Impact of Failure | Risk Level
Redundant Power | Santa Ana | All | Servers without UPS redundant power | 2 - High | 2 - Moderate | 1 - High
Backups | San Diego | N/A | No Backups | 1 - Severe | 1 - High | 1 - High
Redundant V.S | U.S and Asia | N/A | Lack of redundant virtual server | 2 - High | 1 - High | 1 - High
Insufficient V.S | U.S and Asia | N/A | Virtual servers overload | 3 - Moderate | 1 - High | 2 - Medium
Console Servers | All | One per site | Unable to manage remote server console | 3 - Moderate | 2 - Medium | 2 - Medium
Storage | All | N/A | Utilized storage over 75% | 2 - High | 1 - High | 1 - High
Space | S.A and S.D | N/A | Lack of space to add more equipment | 4 - Low | 2 - Moderate | 2 - Medium
Backup Window | U.S | N/A | Full Backup failures, some incrementals | >50% | 1 - Severe | 1 - High
Snapshots | Santa Ana and Asia | N/A | Lack of snapshots as first option for restore | 5-25% | 2 - Moderate | 2 - Medium